## Sheet1
Week |  | Release #
2020-10-03 | Create the cloud based development env
2020-10-11 | Create project Scaffolding | 1
2020-10-19 | Local testing
2020-10-27 | Enable GitHub actions | 1.1
2020-11-04 | Verify remote tests pass
2020-11-12 | Bug fixing and documentation | 1.2
2020-11-20 | Add flask code to project
2020-11-28 | Enable GitHub and the Azure pipelines | 1.3
2020-12-06 | Making predictions
2020-12-14 | Bug fixing | 1.4
2020-12-22 | Documentation
2020-12-30 | Bug fixing and Mainatainace | 1.5
2021-01-07
Top 3 Quarter Goals | Order Prioritized Features | Proposed Difficulty 1-3 (1 easy and 3 is tough) | Feature Category | Project Management Guidelines
Q1 | Setup Azure Cloud Shell | 1 | Tool setup | Demo every monday
Q2 | Configure GitHub actions | 2 | Configuration | Weekly planning after demo
Q3 | Continuous delivery on Azure | 3 | Deployment and documentation | Consumer/Stakeholder Release every 2 weeks
Tickets represents 4 hour - 3 day block of work